## Project Progress
Date | Month | Progress / Activity | Details | Status
2026-09-22 | September | Develop Generative AI Translation - MS Teams Planner |  | Synch in Git
2026-09-22 | September | Synch - Azure Devop XenAnalyticTrans - Local Folder - Github |  | Synch in Git
2026-09-22 | September | Research API gemini |  | Planning
2026-09-22 | September | Research API Deepseek |  | Planning
2026-09-22 | September | Research API Qwen Model |  | Synch in Git
2026-09-22 | September | comparison in budgeting price for all the API key Gen AI |  | Synch in Git
2026-09-22 | September | Setup key from OpenRouter - "OPENROUTER_API_KEY" | insert in cmd prompt - load in visual studio | Synch in Git
2026-09-22 | September | Instruction of limitation rules for Gen AI Translation | Copy from MSTeams Stanley to words | Pending Work
2026-09-22 | September | Developing UI |  | Synch in Git
2026-09-22 | September | Integrating UI - Qwen |  | Synch in Git
2026-09-22 | September | Integrating UI - Claude |  | Synch in Git
2026-09-29 | September | Insert UI Timing to load model and give output |  | Synch in Git
2026-09-29 | September | Comparison in ppt |  | Synch in Git
2026-09-29 | September | Setup API key from Claude API faiz - "ANTHROPIC_API_KEY" |  | Synch in Git
2026-09-29 | September | Setup API key from HuggingFace - "HUGGINGFACE_API_KEY" |  | Synch in Git
2026-09-30 | September | Mapping key column across different table |  | Synch in Git
2026-09-30 | September | Generating excel - UI Merge Table | "D:\XenAnalyticTransl\Reference\Merge Table UI.xlsx" | Synch in Git
2026-10-02 | October | Generate SCL coding synchronize with scenario | when click scenario, SCL language show their respective coding | Synch in Git
2026-10-02 | October | Refine the whole UI. Take note on the improvement suggested by claude | Stop on Friday. Continue on Monday | Pending Work
2026-10-02 | October | Time consumption for the model to load | currently modify. But not have a look at all | In progress
2026-10-05 | October | Hugging Face - Llama : is very bad very slow | thinking to drop out | In progress
2026-10-05 | October | Additon README file |  | Synch in Git
2026-10-06 | October | Troubleshoot MCCTrip On Off problem | Assign On == 1, Off == 0 | Synch in Git
2026-10-07 | October | Add new feature UI Ctrl+F for control find |  | In progress
2026-10-07 | October | Comparison between model |  | In progress
2026-10-07 | October | OpenRouter model unable to load - credit quota problem |  | Pending Work
2026-10-08 | October | Change new key fro OPENROUTER_KEY (PLC_AI_Translator -> XenAITranslator) |  | Synch in Git
2026-10-08 | October | All quota for the all model loaded inside the UI is running out (empty). |  | In progress
2026-10-09 | October | Find the solution of free API key source - Groq |  | Synch in Git
2026-10-09 | October | Setup API key from Groq - "GROQ_API_KEY" |  | Synch in Git
2026-10-09 | October | Seting UI for Groq - Qwen, Llama, GPT |  | Synch in Git
2026-10-09 | October | Problem in Llama Groq |  | Pending Work
2026-10-12 | October | Deisgn the flow chart in ppt for execution and method of finding free API key |  | Synch in Git
2026-10-12 | October | Stop project for a while - focus on XenOptimization |  | Synch in Git
2026-10-16 | October | Change the SCL language to psuedocode. Not apply yet inside UI. Just draft in chatgpt |  | Pending Work
Progress as in 9/10/2026
Develop Dummy UI to integrate gen AI
Experimenting gen AI from 4 model - Qwen, Llama, Claude, ChatGPT
All 4 model free credit is empty, hence the experimentation is stop