Gen AI Integration — Master Plan

24 September 2026  ·  Siti Syaziyah  ·  Project XenAnalyticTransl

# What we are building

PLC Logic Builder is an existing Windows desktop application. An engineer writes a control scenario in natural language, defines terms and properties, and the app maps those terms to real PLC variables.

We are adding a Request AI Translator button that reads the scenario plus its properties and generates SCL (Siemens Structured Text), with an explanation, ready for the engineer to review and save into the project.

| Item | Value |
| --- | --- |
| Host application | PLC Logic Builder, Windows desktop, .NET |
| Target output | SCL — Siemens Structured Text |
| Trigger | Request AI Translator button |
| Input | Scenario text, terms, properties, PLC variable associations |
| Output | Generated logic and explanation, then Copy or Save to Project |
| Repository | D:\XenAnalyticTransl — Azure DevOps (authoritative), GitHub (mirror) |
| Stack | C# / .NET, Visual Studio |

Task numbers throughout refer to planner rows 21–32.

# Open decisions

Three questions are unresolved. The first is the one that matters: it decides the provider and therefore the architecture.

| # | Question | Blocks | Status |
| --- | --- | --- | --- |
| 1 | May scenario text and PLC tag names leave the network? | Provider choice, whole architecture | Open |
| 2 | Must an engineer approve generated code before use? | Depth of validation, UI gating | Open |
| 3 | Does the app already translate deterministically? | Whether AI replaces or supplements | Open |

Phase A below can proceed with invented scenarios while question 1 is open. Nothing reaches production until it is answered.

| Answer to question 1 | Provider | Consequence |
| --- | --- | --- |
| Data may leave | Gemini, Azure AI Foundry, or Qwen via Alibaba Cloud | Low effort, best quality |
| Data may not leave | Self-hosted Qwen3.8-27B or similar | GPU server, ongoing ops, weaker output |

One question to whoever owns the IP or source-control policy: can plant scenario text and PLC tag names be sent to an external AI service?

# Architecture

Four layers, each talking only to its neighbour.

PLC Logic Builder UI        reads panels, shows results

|

v

XenAnalyticTransl.AI        context pack, prompt, validate

|

v

Internal AI service         holds the API key, logs usage

|

v

Model provider

Three rules hold this together.

The UI never calls the model directly. It builds a context pack, hands it to the class library, and displays what comes back.

The API key never ships inside the desktop app. A key in a distributed binary can be extracted in minutes.

Build against the OpenAI-compatible interface. Qwen, Azure AI Foundry, OpenRouter and self-hosted vLLM all speak it, so switching provider is a base URL and a model name rather than a rewrite. This is what stops decision 1 blocking the build.

## The context pack

The single biggest quality lever. The app already holds everything needed.

{

"equipment": "Mtr01",

"target_language": "SCL",

"scenario": "When in Auto Mode, Manual Operation position...",

"terms": [

{ "name": "PLC Initializing", "variable": "Sys_plsInit", "value": 1 }

],

"timers": ["RunFailAlarmTimer", "TripAlarmTimer"]

}

Every highlighted phrase in the scenario becomes a glossary entry. Supply this and the model uses your real variable names. Omit it and the model invents plausible ones, which is worse than an outright failure.

## The response contract

{

"code": "IF AutoMode THEN ...",

"explanation": "Lines 2-6 map the Auto Mode condition...",

"variables_used": ["AutoMode", "ManualOperation", "Sys_plsInit"],

"warnings": ["Scenario does not state behaviour when both..."]

}

The variables_used array feeds the validator. The warnings array surfaces ambiguity in the scenario instead of letting the model guess silently.

# Two safety gates

Neither is optional, because PLC code drives physical equipment.

Identifier validation. Every entry in variables_used must exist in the tag table. No AI involved, just a set lookup. This catches hallucinated variable names, the most dangerous failure mode, because the generated code still compiles and still looks right.

Engineer review. Generated code reaches the project only through an explicit user action. Never auto-save.

Gate 1 is cheap to build and worth building first. Gate 2 depends on the answer to open decision 2.

# Execution

Five phases. Phase A uses invented scenarios on a free API key, so it can start before open decision 1 is settled.

## Phase A — Prove it works (tasks 21, 23, 24)

| Step | Work |
| --- | --- |
| A1 | Write a dummy motor scenario with fake tags, modelled on Mtr01 |
| A2 | Hand-build its context pack as JSON |
| A3 | Write the prompt: system role, SCL dialect, conventions, few-shot examples |
| A4 | Call the model from the console app, print the SCL |
| A5 | Paste the output into TIA Portal. Does it compile? Is the logic right? |
| A6 | Iterate the prompt until output is consistently usable |

Gate: if A5 never produces usable SCL after serious prompt work, stop and report that. Better to find out in week one than in month four.

## Phase B — Make it a component (task 25)

| Step | Work |
| --- | --- |
| B1 | Create the XenAnalyticTransl.AI class library |
| B2 | Move models, prompt builder and client into it |
| B3 | Add schema validation on the response |
| B4 | Add identifier validation against the tag table |
| B5 | Unit tests using recorded responses, so tests need no network and cost nothing |

## Phase C — Measure (task 27)

| Step | Work |
| --- | --- |
| C1 | Build an evaluation set of 30–50 scenarios with known-good output |
| C2 | Score: compiles, logic correct, consistent across repeat runs |
| C3 | Measure latency and cost per call, project monthly cost |
| C4 | Tune, re-run, record the deltas |

## Phase D — Wire the UI (task 26)

| Step | Work |
| --- | --- |
| D1 | Build the context pack from the live panels |
| D2 | Async button handler with progress and cancel |
| D3 | Result panel: generated logic, explanation tab, copy, save |
| D4 | Error and fallback states, never fail silently |
| D5 | Surface unknown identifiers as warnings on the result |

## Phase E — Production (tasks 28–32)

| Step | Work |
| --- | --- |
| E1 | Stand up the internal AI service holding the key |
| E2 | Deployment and environment configuration |
| E3 | Server-side integration and load testing |
| E4 | User acceptance testing with 3–5 engineers |
| E5 | Documentation: user guide, ops runbook, prompt rationale |

# Where to start

Roughly one day of work, and it tells you more than a month of design.

☐  Get a free Gemini key at aistudio.google.com, about two minutes

☐  Write one dummy motor scenario with invented tags

☐  Build its context pack by hand

☐  Write the prompt and call the model from the console app

☐  Paste the SCL into TIA Portal and see whether it compiles

The last step is the real gate. If carefully-prompted SCL never compiles, that is worth knowing in week one.

Use invented scenarios, not real plant data. Free API tiers generally allow the provider to use submitted content for product improvement, so the free tier is for learning the API, not for plant intellectual property.

# Decision log

Record choices here as they are made, with the date and the reason.

| Date | Decision | Reason |
| --- | --- | --- |
| 2026-09-22 | Repo named XenAnalyticTransl, DevOps authoritative, GitHub mirror | Team server is DevOps |
| 2026-09-22 | Branch main | Matches GitHub default and DevOps convention |
| 2026-09-24 | Build against the OpenAI-compatible interface | Keeps the provider choice open and reversible |
| pending | May plant data leave the network? |  |
| pending | Model provider |  |
| pending | Is engineer review of generated code mandatory? |  |